## Slide 1
CARPENTERS FIJI
CREMS
Technology, pilot scope
and semester delivery plan
Carpenters Rentals + Carptrac
Client meeting • 10 August 2026
Notes: Open by confirming the purpose: agree the platform foundation, the first two divisions and the delivery baseline through 30 October.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]

## Slide 2
CREMS / CLIENT MEETING
02
Today we are confirming one practical delivery baseline
TWO PILOT DIVISIONS
Carpenters Rentals
Carptrac
ONE MODULAR PLATFORM
Shared capabilities,
configurable rules
TWELVE WEEKS
10 August to
30 October 2026
Outcome
A tested rental and maintenance MVP that supports vehicle and heavy-equipment workflows while leaving a clean path for future Carpenters divisions.
Notes: Use this as the meeting anchor. The team is not proposing separate systems for each division; it is proposing one reusable platform with two initial operating contexts.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]

## Slide 3
CREMS / CLIENT MEETING
03
Two pilot divisions prove the model across different operations
Carpenters Rentals
Vehicle-led booking, agreements, pickup, return, damage evidence and fleet utilisation.
Carptrac
Equipment availability, hour-meter tracking, personnel requirements, inspections and maintenance.
What this validates
• One customer foundation
• One asset lifecycle
• Different operational rules
• Division and branch controls
• Reusable reporting
Notes: Explain that these divisions were chosen because together they test both straightforward vehicle rental and more specialised equipment operations.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]

## Slide 4
CREMS / CLIENT MEETING
04
Shared modules reduce duplication; rules stay configurable
SHARED CREMS CORE
Identity • Customers • Branches • Assets • Bookings • Agreements • Inspections • Maintenance • Notifications • Audit • Reports
RENTALS CONFIGURATION
Vehicle categories
Licence and driver details
Fuel and odometer
Daily rental and return rules
CARPTRAC CONFIGURATION
Equipment categories
Hour-meter readings
Operator or technician rules
Equipment maintenance controls
FUTURE DIVISIONS
Add a division
Enable capabilities
Configure its workflow
Reuse the core platform
Notes: Describe the architecture in business terms. Shared modules are built once; division settings decide which workflow and data fields apply.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]

## Slide 5
CREMS / CLIENT MEETING
05
The MVP covers the full rental transaction lifecycle
1
Control access
Staff authentication and Administrator, Branch Manager and Rental Officer permissions.
2
Prepare the rental
Vehicle and equipment masters, customers, reservations and real-time availability.
3
Release the asset
Agreement generation, allocation, QR identification and inspection-based check-out.
4
Close the rental
Return processing, inspections, damage reporting and maintenance request creation.
A single traceable flow: reservation → agreement → allocation → check-out → return → maintenance decision
Notes: Emphasise end-to-end traceability. Each transaction changes availability and creates evidence for the next operational step.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]

## Slide 6
CREMS / CLIENT MEETING
06
Management visibility is built into the same operational data
DASHBOARD
Available
Currently rented
Under maintenance
Upcoming bookings
Overdue rentals
Revenue summary
REPORTS
Rental history
Fleet utilisation
Equipment utilisation
Maintenance report
Revenue report
Overdue rentals
Customer rental history
Controls
Email notifications
Preventive maintenance reminders
QR / barcode identification
Critical transaction audit logs
Notes: Connect reporting to the operational workflow: dashboards and reports are not a separate data-entry exercise; they are generated from booking, return and maintenance records.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]

## Slide 7
CREMS / CLIENT MEETING
07
The selected stack is secure, maintainable and team-ready
EXPERIENCE
React + TypeScript + Vite + Material UI
Responsive staff and customer interfaces
APPLICATION
ASP.NET Core 10 Web API
Business rules, workflows and integrations
IDENTITY
ASP.NET Core Identity
Authentication, recovery and role-based access
DATA
SQL Server 2022 + Entity Framework Core
Transactions, relationships and migrations
DELIVERY
Docker + GitHub + Postman
Consistent setup, collaboration and API testing
SERVICES
SMTP / email provider + PDF + QR libraries
Notifications, agreements and asset identification
Notes: Confirm that this is the stack already used by the project. Explain that Docker supports the team’s mix of macOS and Windows development environments.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]

## Slide 8
CREMS / CLIENT MEETING
08
Weeks 1–6 establish the secure rental foundation
01
10–14 Aug
Scope, schema, stack and authentication
02
17–21 Aug
Divisions, branches, roles and access scope
03
24–28 Aug
Vehicle and equipment master management
04
31 Aug–4 Sep
Individual and corporate customer records
05
7–11 Sep
Availability, reservations and conflict prevention
06
14–18 Sep
Agreements, approvals and asset allocation
Notes: Week 1 is the foundation sprint. From Week 2 onward, each sprint adds a demonstrable increment on top of the existing platform.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]

## Slide 9
CREMS / CLIENT MEETING
09
Weeks 7–12 complete operations, insight and handover
07
21–25 Sep
QR-assisted check-out and condition inspections
08
28 Sep–2 Oct
Return, damage evidence and charge decisions
09
5–9 Oct
Maintenance schedules, jobs, costs and reminders
10
12–16 Oct
Dashboard, utilisation and management reports
11
19–23 Oct
Notifications, audit, integration and security testing
12
26–30 Oct
Client UAT, defect correction, training and handover
Notes: The last two sprints protect integration and acceptance time. New scope should not displace security, UAT, documentation or handover activities.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]

## Slide 10
CREMS / CLIENT MEETING
10
Every sprint ends with working evidence, not only code
MONDAY
Plan the sprint
and confirm acceptance
TUE–WED
Develop, review
and unit test
THURSDAY
Integrate frontend,
API and database
FRIDAY
Demonstrate, record
feedback and improve
Definition of done
Accepted criteria • integrated frontend and API • authorization tested • migration included • peer reviewed • demonstration recorded
Notes: This slide demonstrates delivery discipline. Each Friday provides evidence and an opportunity for client feedback before the next increment.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]

## Slide 11
CREMS DELIVERY BASELINE
A focused pilot now.
A reusable platform next.
14 AUG
Scope, stack and architecture
11 SEP
Booking workflow
09 OCT
Rental and maintenance lifecycle
23 OCT
Integrated release candidate
30 OCT
UAT and handover
Carpenters Rentals + Carptrac
Notes: Close on the delivery commitment: the two pilot divisions create a credible semester outcome and validate the architecture for future divisions.
[Sources]
- Client/project team scope and timeline supplied 10 August 2026.
[/Sources]